PROJECT PROGRESS REPORT

1.PROJECT DETAILS

Project Name		:	EC – Matatiele Nature Reserve Gateway Office and Eco-Tourism

Complex

Implementer		:	Farci Trading cc

Project Duration	:	12 months

2.	PROJECT DESCRIPTION

The project is aimed at constructing the administration facility for conservation and ecotourism functions of the municipality. The project will encompass Administration Block and Art Craft retail & display area with kiosk, guests & personnel ablutions facilities, parking area, pathways, fencing and re-vegetation.

3.	PROJECT BUDGET

The approved project budget is R 7,000,000.00

4.	DELIVERABLES

| Deliverable 1 : | Pedestrian Walkway |
| --- | --- |
| Deliverable 2 : | Sewer Reticulation |
| Deliverable 3 : | Parking Bays |
| Deliverable 4 : | Water Reticulation |
| Deliverable 5 : | Administration Block & Art Centre |
| Deliverable 6 : | Fencing |
| Deliverable 7 : | Guard House |
| Deliverable 8 : | Re-vegetation and Landscaping |

5.	JOB CREATION

| Category | Planned No. of people | Rate | No of people employed to date |
| --- | --- | --- | --- |
| Clerical | 2 | R 123.00 | 2 |
| Labourers | 77 | R 82.00 | 36 |
| Semi-skilled | 6 | R 103.00 | 6 |
| Skilled | 4 | R 123.00 | 4 |
| Supervisors | 2 | R 144.00 | 2 |
| TOTAL | 82 |  | 50 |

***	Initially project  employed all 82 beneficiaries but due to the delays and works being

on hold some beneficiaries have not reported to work yet. Only 50 have reported

back to work; some advised that they will be available from Monday, 01 February 2015

whilst others have resigned. We are busy with replacing them.

6.	SKILLS DEVELOPMENT

The following non-accredited training courses have been conducted:

| Courses | No. of Trainees |
| --- | --- |
| First Aid | 20 |
| Health & Safety | 82 |
| Life Skills | 82 |
| Environmental Awareness | 82 |
| Personal Finance | 82 |
| HIV/AIDS | 82 |

8.	PROGRESS TO DATE

- Site Clearance is 100% complete

- Administration Block  and Arts Craft Centre: Excavations  are 100% complete

- Guard House: Foundations are 100% complete; Superstructure is 50% complete

- Water reticulation: Drilling and installation of borehole is 90%

- Fencing: Site clearance and Digging of holes is 100% complete; Installation is 55%

Complete

7.	PHOTOS SHOWING CURRENT PROGRESS

- Fencing – Welded Mesh

- Guard House

- Admin Block and Arts Craft Centre  – Excavations for foundations and Fencing