## Slide 1: In preparing the Activity Plan

## Slide 2: Keep in mind:
What you set out to achieve as a group:
To overcome TFCA challenges through shared learning, knowledge management and collaboration
By:
  Determining common solutions to common challenges
  Sharing experiences within and across TFCAs
  Developing a regional repository of TFCA related information

## Slide 3: Incomplete activities from last time
Consolidate membership
  Nominations to core membership & champions
Network description document
  Comments & finalise & disseminate
Portal:
  Feedback on structure to improve portal
  Content population of public & restricted portals
  Uploading existing documentation relevant for each TFCA
Stakeholder mapping
  Complete stakeholder mapping exercise per TFCA
  Stakeholder engagement guidelines for the TFCA Network
Other activities to consolidate functional Network?
  Capacity building for online facilitators & administrators
  Sustainable financing for Network activities

## Slide 4: Prioritisation from yesterday
Priority Theme | Envisioned Products | Ongoing activities/products which might be useful
Governance | Framework for effective TFCA management & governance Amendment of SADC Protocol on Wildlife & Conservation to include TFCA issues | SADC TFCA Guideline Development
Community Involvement | Draft SADC policy on community involvement | Guidelines on tourism concessions
Cross border law enforcement | Standard Operating Procedures | 
Sustainable financing | SADC TFCA Sustainable Financing Strategy | GIZ/SADC Sustainable Financing Strategy for /Ai-/Ais-Richtersveld TP

## Slide 5: Group work – 5 groups
Governance
Community Involvement
Sustainable financing
Cross border law enforcement
Carry over & consolidation

## Slide 6: Theme: Product:
Activity | Deliverable | User of the deliverable | Timeline | Responsibility | Funding source | External Stakeholder
*Delivered to whom could be for example:
  Restricted portal for consumption of TFCA network members
  Public portal for general public
  Specific TFCA institutions
  National govts
  SADC Secretariat